DrugEye

Z-AI Pharmacy Platform

Production Readiness & Full Development Plan

| Version | 1.0 — April 2026 |
| --- | --- |
| Status | Pre-Production — Active Development |
| Prepared By | Claude (Anthropic) — Code Audit & Planning |

# 1. Executive Summary

DrugEye is a clinical decision support platform (CDSS) built for UAE healthcare professionals. The codebase represents a strong, well-architected prototype with a solid Next.js 16 / Prisma / PostgreSQL stack, comprehensive clinical data pipelines, and an AI-powered chat system. However, a full code audit reveals several critical issues that must be resolved before production launch.

This document provides: a complete catalogue of every weakness found in the audit; prioritised fix plans with specific code-level actions; a phased development roadmap from current state to production; all required environment variables; and success metrics. The plan is structured for a small team and can be completed in approximately 8–10 weeks.

Audit Summary Total files audited: 50+ ¦ Critical issues: 8 ¦ High issues: 12 ¦ Medium issues: 9 ¦ Total mock data replacements: 6 ¦ Unprotected API routes: 14+

# 2. Complete Weakpoint Audit

Every issue found during the full source code audit is catalogued below, grouped by category.

## 2.1 Mock Data & Placeholder Issues

| Issue / Weakpoint | Severity | Phase | Fix / Action |
| --- | --- | --- | --- |
| Dashboard stats (activeInteractions, recentSearches) | Critical | Phase 1 | Replace Math.random() with real DB counts from UserSearchHistory and DrugInteraction tables |
| Analytics API (interactionsChecked, dosageCalculations, activeUsers) | Critical | Phase 1 | Add AuditLog tracking to chat/interaction/dosage routes; aggregate for real counts |
| Admin Subscriptions page | Critical | Phase 1 | Replace hardcoded setTimeout() mock array with real /api/user/subscription DB query |
| Reports analytics — topDrugs searches count | High | Phase 1 | Track search events in UserSearchHistory; query top N by frequency |
| Reports analytics — drugTrend (0.95 multiplier) | High | Phase 1 | Store historical drug count snapshots; compute real period-over-period diff |
| Email service fallback mock-message-id | Medium | Phase 2 | Require EMAIL_SERVER_HOST in prod; add startup check; throw if missing |

## 2.2 Security & Authentication Issues

| Issue / Weakpoint | Severity | Phase | Fix / Action |
| --- | --- | --- | --- |
| No Next.js middleware.ts — all (app) routes unprotected | Critical | Phase 1 | Create /src/middleware.ts with NextAuth matcher for /(app)/* and /api/* routes |
| 14+ API routes have no auth check | Critical | Phase 1 | Apply requireAuth() to: /api/drugs/*, /api/chat, /api/reports/*, /api/ai/* |
| Admin pages use client-side redirect only | Critical | Phase 1 | Add server-side session check + role guard in admin page server components |
| Rate limiter built but never applied to any route | High | Phase 1 | Apply checkRateLimit() to /api/chat (10/min), /api/drugs/search (100/min), /api/auth (5/min) |
| typescript.ignoreBuildErrors: true in next.config.js | High | Phase 1 | Remove flag; fix all TypeScript errors before prod build |
| No CSRF protection on POST routes | High | Phase 2 | Use NextAuth built-in CSRF token or add custom header check |
| No input sanitization on drug search query param | Medium | Phase 2 | Add zod schema validation to all GET query params; strip SQL metacharacters |
| GitHub OAuth secrets may be undefined (non-null assertion) | High | Phase 1 | Add env var validation at startup; throw descriptive errors if missing |

## 2.3 Analytics & Observability

| Issue / Weakpoint | Severity | Phase | Fix / Action |
| --- | --- | --- | --- |
| Performance API logs to console.log only | High | Phase 2 | Integrate Vercel Analytics (already installed) or connect Sentry via SENTRY_DSN env var |
| Error API (/api/errors) is a stub — no real sink | High | Phase 2 | Connect @sentry/nextjs; instrument error boundary; forward client errors to Sentry |
| Google Analytics gtag integrated but GA_ID not validated | Medium | Phase 2 | Add NEXT_PUBLIC_GA_ID check; no-op gracefully if absent; document in .env.example |
| No audit logging on clinical actions (drug lookup, interaction check) | High | Phase 2 | Write to AuditLog table on every drug lookup, interaction check, and dosage calc in API routes |
| useSessionTracking hook: getUserRole / getSubscriptionTier undefined | Medium | Phase 2 | Implement helpers reading from next-auth session; pass userId to analytics events |

## 2.4 Architecture & Code Quality

| Issue / Weakpoint | Severity | Phase | Fix / Action |
| --- | --- | --- | --- |
| Multiple local GlassCard / Badge2 components duplicated across 6+ pages | Medium | Phase 2 | Extract shared styled components to /src/components/ui/glass-card.tsx and badge.tsx |
| AppLayout.tsx creates new PrismaClient per invocation in some API routes | High | Phase 1 | Audit all route files; replace local `new PrismaClient()` with shared db import from @/lib/db |
| Inconsistent design system: some pages dark (#000 bg), others light (white) | Medium | Phase 3 | Define theme contract; apply next-themes consistently across all (app) pages |
| Error handling in search/pregnancy/dosage pages: empty catch blocks | High | Phase 2 | Add toast error notifications (sonner already installed); log to /api/errors endpoint |
| No loading skeleton on initial dashboard data fetch | Low | Phase 3 | Use existing SkeletonList component for dashboard cards |
| Typo in route: /tasklisst (double s) | Low | Phase 3 | Rename to /tasklist; add redirect from old path |
| images.remotePatterns allows pravatar.cc and unsplash — should be restricted | Medium | Phase 2 | Restrict to internal/CDN domains only in production next.config.js |

## 2.5 Production Infrastructure Gaps

| Issue / Weakpoint | Severity | Phase | Fix / Action |
| --- | --- | --- | --- |
| No .env.example file in repo | High | Phase 1 | Create .env.example with all 20+ required variables; document each one |
| No database connection pooling config for Neon serverless | High | Phase 1 | Add pool_timeout and max_connections params to DATABASE_URL for Neon |
| vercel.json missing function timeout and memory config | Medium | Phase 2 | Add maxDuration:60 for AI routes; regions:["iad1"] for Neon latency |
| No health check endpoint | Medium | Phase 2 | Create /api/health returning DB ping, version, and uptime |
| next-pwa service worker active but no offline fallback page | Low | Phase 3 | Create /public/offline.html; configure runtimeCaching in next.config.js |
| No database backup / snapshot strategy documented | High | Phase 2 | Configure Neon daily automated backups; document recovery procedure |

# 3. Phased Development Roadmap

The plan is divided into four phases, each building on the last. Phases 1 and 2 are prerequisites for production launch. Phases 3 and 4 deliver feature completeness and scale.

| Phase | Timeline | Focus | Exit Criteria |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1–2 | Critical security & mock data fixes | Zero unprotected routes; zero Math.random() stats |
| Phase 2 | Weeks 3–5 | Observability, error handling, real analytics | Sentry live; all API routes audited & validated |
| Phase 3 | Weeks 6–7 | UI consistency & PWA hardening | Unified design system; all pages theme-consistent |
| Phase 4 | Weeks 8–10 | Scale, CI/CD, production launch | CI green; Vercel prod deployed; 99.9% uptime target |

## Phase 1 — Security Hardening & Mock Elimination (Weeks 1–2)

These are blocking issues. Nothing should go to production until Phase 1 is complete.

| Task | Owner | Est. Effort |
| --- | --- | --- |
| Create /src/middleware.ts with NextAuth session guard for all (app) and API routes | Backend Dev | 4h |
| Apply requireAuth() to all 14+ unprotected API routes | Backend Dev | 6h |
| Add server-side role guard to /admin/* page server components | Backend Dev | 3h |
| Apply checkRateLimit() from existing lib/rate-limit.ts to chat, search, auth routes | Backend Dev | 3h |
| Replace Math.random() in dashboard/page.tsx with real DB aggregates | Backend Dev | 2h |
| Replace Math.random() in /api/reports/analytics/route.ts with AuditLog queries | Backend Dev | 4h |
| Replace hardcoded mock subscriptions in admin page with real DB fetch | Backend Dev | 2h |
| Replace all new PrismaClient() instances in API routes with shared db import | Backend Dev | 2h |
| Remove typescript.ignoreBuildErrors: true; fix all resulting TS errors | Backend Dev | 8h |
| Create .env.example with all required variables documented | DevOps | 2h |
| Add startup env validation (throw on missing critical vars) | Backend Dev | 2h |

## Phase 2 — Observability, Error Handling & Data Integrity (Weeks 3–5)

| Task | Owner | Est. Effort |
| --- | --- | --- |
| Integrate @sentry/nextjs for server-side and client-side error capture | Backend Dev | 4h |
| Wire client error boundary to /api/errors → Sentry | Frontend Dev | 3h |
| Add AuditLog writes to drug lookup, interaction check, dosage calc routes | Backend Dev | 4h |
| Implement real search event tracking in UserSearchHistory from search page | Frontend Dev | 3h |
| Build /api/health endpoint with DB ping, version, uptime | Backend Dev | 2h |
| Add zod validation to all API GET query params (q, limit, page, etc.) | Backend Dev | 4h |
| Add try/catch + sonner toast notifications to all empty catch blocks in pages | Frontend Dev | 4h |
| Fix getUserRole / getSubscriptionTier helpers in use-analytics.ts | Frontend Dev | 2h |
| Configure Vercel Analytics tracking events for drug search and AI chat | Frontend Dev | 2h |
| Add CSRF header validation to all POST/PUT/DELETE API routes | Backend Dev | 3h |
| Configure Neon daily backup; document recovery runbook | DevOps | 3h |
| Update vercel.json with maxDuration, memory, and region settings | DevOps | 2h |
| Implement email health check — require EMAIL_SERVER_HOST in production | Backend Dev | 2h |

## Phase 3 — UI Consistency, PWA & Design System (Weeks 6–7)

| Task | Owner | Est. Effort |
| --- | --- | --- |
| Extract GlassCard and Badge2 into /src/components/ui/glass-card.tsx | Frontend Dev | 3h |
| Apply next-themes dark/light consistently to all (app) pages | Frontend Dev | 8h |
| Add SkeletonList loading states to dashboard cards and search results | Frontend Dev | 4h |
| Create /public/offline.html PWA fallback page; configure runtimeCaching | Frontend Dev | 3h |
| Rename /tasklisst route to /tasklist; add 301 redirect | Frontend Dev | 1h |
| Restrict next.config.js images.remotePatterns to internal domains only | Backend Dev | 1h |
| Audit Arabic (RTL) layout on all pages; fix alignment issues | Frontend Dev | 4h |
| Add pagination to admin subscriptions table | Frontend Dev | 3h |
| Improve drug detail page: show all sideEffects, interactions, ICD-10 codes | Frontend Dev | 4h |

## Phase 4 — CI/CD, Load Testing & Production Launch (Weeks 8–10)

| Task | Owner | Est. Effort |
| --- | --- | --- |
| Set up GitHub Actions workflow: lint + type-check + vitest on every PR | DevOps | 4h |
| Add Prisma migration safety check to CI (shadow DB validation) | DevOps | 3h |
| Write integration tests for /api/drugs/search, /api/chat, /api/drugs/interactions | QA | 8h |
| Load test AI chat endpoint (target: 10 concurrent, <3s p95) | QA | 4h |
| Add Vercel edge config for feature flags (AI chat kill-switch) | DevOps | 3h |
| Clinical pharmacist validation sign-off on drug data accuracy | Clinical | 16h |
| UAE MOH compliance review and legal disclaimer finalisation | Clinical/Legal | 8h |
| Production deployment with zero-downtime migration strategy | DevOps | 4h |
| Post-launch monitoring setup: alerts for error rate, latency, DB connections | DevOps | 3h |

# 4. Mock-to-Real Replacement — Code Guide

This section provides exact file paths, the current mock code, and the production replacement logic for each instance.

## 4.1 Dashboard Stats (dashboard/page.tsx)

File src/app/(app)/dashboard/page.tsx — lines 62–65

Current mock code:

activeInteractions: Math.floor(Math.random() * 50) + 10,

recentSearches: Math.floor(Math.random() * 100) + 20

Replacement logic:

- Create /api/drugs/stats/dashboard route that runs:

  - activeInteractions: db.drugInteraction.count({ where: { createdAt: { gte: startOfToday } } })

  - recentSearches: db.userSearchHistory.count({ where: { userId: session.user.id, createdAt: { gte: last7days } } })

  - totalPatients: db.patient.count({ where: { clinicianId: session.user.id } })

## 4.2 Analytics API (reports/analytics/route.ts)

File src/app/api/reports/analytics/route.ts — lines 52–60

Replacement: Add an AuditLog write to each clinical endpoint:

- In /api/chat/route.ts: await db.auditLog.create({ data: { userId, action: "AI_CHAT", resourceType: "chat" } })

- In /api/drugs/interactions/route.ts: write AuditLog with action: "INTERACTION_CHECK"

- In /api/drugs/dosage/route.ts: write AuditLog with action: "DOSAGE_CALC"

- Analytics route then queries: db.auditLog.count({ where: { action: "INTERACTION_CHECK", createdAt: { gte: startDate } } })

## 4.3 Admin Subscriptions (admin/subscriptions/page.tsx)

File src/app/(app)/admin/subscriptions/page.tsx — lines 45–52

Replacement: Convert to async server component or add useEffect with real fetch:

- Fetch from: GET /api/admin/subscriptions?page=1&limit=20

- New route joins Subscription + User tables: db.subscription.findMany({ include: { user: true }, orderBy: { createdAt: "desc" } })

- Add server-side role guard: if session.user.role !== "admin" redirect("/")

- Add real revenue calculation: sum of all active subscription amounts by planId

## 4.4 Auth — Middleware Route Protection

File Create new file: src/middleware.ts

Production middleware pattern:

- Export config matcher: ["/(app)/:path*", "/api/drugs/:path*", "/api/chat/:path*", "/api/reports/:path*", "/api/ai/:path*", "/api/admin/:path*"]

- Use withAuth from next-auth/middleware

- Add role check in middleware callbacks: token.role === "admin" for admin paths

- Public paths to exclude: /api/auth/:path*, /api/drugs/search (for demo), /landing, /auth/:path*

## 4.5 Rate Limiting — Apply Existing Implementation

File Rate limiter exists at src/lib/rate-limit.ts — just needs to be called

Add to each route handler:

- AI chat route: checkRateLimit(userId || ip, "chat") — limit: 10 requests/minute

- Drug search: checkRateLimit(userId || ip, "search") — limit: 100 requests/minute

- Auth routes: checkRateLimit(ip, "auth") — limit: 5 requests/minute

- Return NextResponse.json({ error: "Rate limit exceeded" }, { status: 429 }) on failure

# 5. Required Environment Variables

All variables must be set in Vercel project settings for production. Create a .env.example file in the repo root with all keys (values redacted) for developer onboarding.

## 5.1 Database

| Environment Variable | Description / Example |
| --- | --- |
| DATABASE_URL | Neon PostgreSQL pooled connection string (pgbouncer mode) |
| DIRECT_URL | Neon direct (non-pooled) URL for migrations only |

## 5.2 Authentication

| Environment Variable | Description / Example |
| --- | --- |
| NEXTAUTH_SECRET | Strong random secret — min 32 chars (use: openssl rand -base64 32) |
| NEXTAUTH_URL | Production URL e.g. https://drugeye.ae |
| GITHUB_CLIENT_ID | OAuth App client ID from github.com/settings/developers |
| GITHUB_CLIENT_SECRET | OAuth App client secret from github.com/settings/developers |

## 5.3 AI Services

| Environment Variable | Description / Example |
| --- | --- |
| GROQ_API_KEY | Groq API key from console.groq.com |
| OPENAI_API_KEY | OpenAI API key from platform.openai.com |

## 5.4 Email

| Environment Variable | Description / Example |
| --- | --- |
| EMAIL_SERVER_HOST | SMTP host e.g. smtp.sendgrid.net or smtp.mailgun.org |
| EMAIL_SERVER_PORT | 587 (TLS) or 465 (SSL) |
| EMAIL_SERVER_USER | SMTP username / API key username |
| EMAIL_SERVER_PASSWORD | SMTP password or API key |
| EMAIL_SERVER_SECURE | "true" for SSL port 465, "false" for TLS port 587 |
| EMAIL_FROM | "DrugEye" <noreply@drugeye.ae> |

## 5.5 Monitoring & Analytics

| Environment Variable | Description / Example |
| --- | --- |
| SENTRY_DSN | Sentry project DSN from sentry.io/settings/projects |
| SENTRY_AUTH_TOKEN | Sentry auth token for source map uploads during build |
| NEXT_PUBLIC_GA_ID | Google Analytics 4 Measurement ID (G-XXXXXXXXXX) |
| PERFORMANCE_WEBHOOK_URL | Optional: webhook URL for custom performance metrics sink |

## 5.6 Application

| Environment Variable | Description / Example |
| --- | --- |
| NEXT_PUBLIC_APP_URL | Public base URL used for email links e.g. https://drugeye.ae |
| NODE_ENV | "production" — set automatically by Vercel |

# 6. Production Success Metrics

| Metric | Target | How to Measure |
| --- | --- | --- |
| API response time | <200ms p95 for drug search | Vercel Function logs + Analytics |
| AI chat latency | <3s p95 for first token | Groq dashboard + AuditLog timestamps |
| Error rate | <0.1% of all API requests | Sentry error rate dashboard |
| Uptime | 99.9% monthly | Vercel uptime + UptimeRobot alerts |
| Data accuracy | >99.5% match vs verified pharmacopeia | Monthly clinical audit by pharmacist |
| Auth security | Zero unauthorised data access | Sentry + AuditLog anomaly review |
| Drug database freshness | Updated within 7 days of MOH changes | Automated diff in CI pipeline |
| WAU engagement | >70% of registered users active weekly | UserSearchHistory + GA4 events |
| Build time | <5 min in CI | GitHub Actions duration |
| TypeScript errors | 0 in production build | CI type-check step must pass |

# 7. Platform Strengths — What Is Already Production-Quality

The following areas are well-implemented and require no rework before launch:

- Drug database & ETL pipelines: Comprehensive multi-source ingestion (FDA, SIDER, DailyMed, ICD-10, UAE MOH) with 21,885+ drugs

- Prisma schema: 654-line schema is well-normalised; covers Users, Patients, Drugs, Interactions, SideEffects, ICD10, Subscriptions, AuditLog, and RateLimit

- AI chat architecture: Proper tool-use pattern with Groq streaming; 6 clinical tools (drugLookup, interactionChecker, sideEffects, pregnancySafety, diseaseInfo, treatment)

- Drug interaction checker: Solid normalisation logic with fuzzy name matching across generic and brand names

- User search history API: Fully implemented with auth guard, pagination, and Zod validation — already production-ready

- Dosage calculator API: Real DB queries with external data enrichment fallback; filters for drugs with baseDoseMgPerKg data

- MOH Alerts: Real database-backed endpoint with POST admin creation; connected to MohAlertBanner component

- Pregnancy safety page: Fetches from real /api/drugs/pregnancy endpoint with FDA category filtering

- Email service: Nodemailer integration is structurally correct; only needs EMAIL_SERVER_HOST env var to activate

- NextAuth: Properly configured with Prisma adapter, JWT strategy, role-aware session callbacks, and bcrypt password hashing

- Rate limiter implementation: Full sliding window rate limiter in src/lib/rate-limit.ts backed by the DB — just needs to be applied

- Favorites, patient management, and subscription APIs: All properly auth-guarded with Zod validation

- i18n foundation: Full Arabic/English translation object in AppProvider; RTL flag in place

# 8. Pre-Launch Checklist

| ☐ | Phase 1 complete: all critical security issues resolved |
| --- | --- |
| ☐ | Phase 2 complete: Sentry live, AuditLog writing, no empty catches |
| ☐ | TypeScript build passes with zero errors |
| ☐ | All environment variables set in Vercel project |
| ☐ | Database migrations applied to production Neon DB |
| ☐ | Admin seed script run to create first admin user |
| ☐ | Email service tested end-to-end (password reset flow) |
| ☐ | Rate limiting verified under load (curl loop test) |
| ☐ | Clinical pharmacist sign-off on drug data quality |
| ☐ | Legal disclaimer reviewed and approved |
| ☐ | Privacy policy and terms of service pages complete |
| ☐ | robots.txt and sitemap.ts verified for SEO |
| ☐ | Vercel deployment with custom domain configured |
| ☐ | SSL certificate active on production domain |
| ☐ | Post-launch monitoring alerts configured in Sentry and Vercel |
| ☐ | Backup/restore procedure tested on staging DB |
| ☐ | Load test passed (50 concurrent users, <500ms p95) |
| ☐ | GDPR/HIPAA data handling review completed |

DrugEye — UAE MOH Pharmaceutical Intelligence Platform | Confidential | April 2026